## Exterior Slabs
Inspection of Barrier Cable Installation Through or Attached to Concrete Columns | [17 empty] | Page _______ of _________
|  |  | Project Name | [10 empty] | Project #
|  |  | Site Address | [10 empty] | Date
Jack Serial #
|  |  | General contractor | [10 empty] | Gauge Serial #
|  |  | Barrier cable supplier | [6 empty] | Date of For Construction BC installation drawings
|  |  | Installation company | [10 empty] | Special remarks
Installed by
Inspected by
Barrier Cables at the exterior on lines | [7 empty] | and
|  |  | Specified spacing between cables | Specified distance from top of slab to middle of topmost cable | Surface mounted steel members secured to columns per dwgs | Job site or pre-installed anchorages have fully seated wedges | Stressed to BC force indicated on dwgs | Back stressed to force indicated on dwgs | Restoration of corrosion protection after back stressing | Strand tails finished | Sealing of sleeves in columns | Initials of inspector or installer | Date | Holes: Topmost cable #1 Bottom cable # varies | Non-compliance items corrected | Initials of inspector or installer | Date
| & | to
|  |  |  | Specified Jacking Force (kips): |  |  |  |  | Specified Gauge Reading (psi): |  |  |  |  | Specified Back stressing Force (kips): |  |  | Cable Numbers:
Level
Level
Level
Level
Level
| & | to
Level
Level
Level
Level
Level
Spacing / Height
Fixed-End
Finishing
Inspection
Non-compliance / notes
Follow-up (if needed)
Notes
Stressing

## Example Exterior Slabs
Inspection of Barrier Cable Installation Through or Attached to Concrete Columns | [19 empty] | Page _______ of _________
[5 empty] | Project Name | [10 empty] | Project #
[5 empty] | Site Address | [10 empty] | Date
Jack Serial #
[5 empty] | General contractor | [10 empty] | Gauge Serial #
[5 empty] | Barrier cable supplier | [6 empty] | Date of For Construction BC installation drawings
[5 empty] | Installation company | [10 empty] | Special remarks
Installed by
Inspected by
Barrier Cables at the exterior on lines | [8 empty] | D | and | A
[5 empty] | Specified spacing between cables | Specified distance from top of slab to middle of topmost cable | Surface mounted steel members secured to columns per dwgs | Job site or pre-installed anchorages have fully seated wedges | Stressed to BC force indicated on dwgs | Back stressed to force indicated on dwgs | Restoration of corrosion protection after back stressing | Strand tails finished | Sealing of sleeves in columns | Initials of inspector or installer | Date | Holes: Topmost cable #1 Bottom cable # varies | Non-compliance items corrected | Initials of inspector or installer | Date
D | & | 1 | to | 23
[6 empty] | Specified Jacking Force (kips): | 3.5 |  |  |  | Specified Gauge Reading (psi): | 900 |  |  |  | Specified Back stressing Force (kips): | 33 |  | Cable Numbers: | #1 - #6 and #10 - #11
Level |  | 2 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | N/A | DJS | 2014-10-26 | Cable #7 did not get epoxy coating. | Yes | PS | 2013-11-15 | Cable was coated with epoxy.
Level |  | 3 |  |  | Yes | No | No | Yes | Yes | Yes | Yes | Yes | N/A | DJS | 2014-10-26 | Angles at lines 10 thru 14 were too low. | Yes | DJS | 2013-11-28 | All 5 angles were raised 4" so cable #1 was 42".
Level |  | 4 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | N/A | DJS | 2014-10-26
Level |  | 5 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | N/A | DH | 2013-11-02
Level |  | 6 |  |  | Yes | Yes | Yes | Yes | Yes | No | No | Yes | N/A | DH | 2013-11-02 | Cable #1 not back stressed & c. p. restored. | Yes | DH | 2013-11-03 | Cable was back stressed and epoxy coated.
A | & | 1 | to | 23
Level |  | 2 |  |  | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | N/A | DJS | 2014-10-28 | Line 23 tube not welded correctly to steel plate. | Yes | PS | 2013-11-21 | Tube was cont. welded to embed on both sides.
Level |  | 3 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | N/A | DJS | 2014-10-28
Level |  | 4 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | N/A | DJS | 2014-10-28
Level |  | 5 |  |  | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | N/A | DH | 2013-11-02 | Inter. angle at line 14 had only one anchor bolt. | Yes | DH | 2013-11-03 | Additional anchor bolt was added at the bottom.
Level |  | 6 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | N/A | DH | 2013-11-02
1
23
D
A
Spacing / Height
Fixed-End
Finishing
Inspection
Non-compliance / notes
Follow-up (if needed)
Notes
N
Stressing

## Ramped Slabs
Inspection of Barrier Cable Installation Through or Attached to Concrete Columns | [16 empty] | Page _______ of _________
|  | Project Name | [10 empty] | Project #
|  | Site Address | [10 empty] | Date
Jack Serial #
|  | General contractor | [10 empty] | Gauge Serial #
|  | Barrier cable supplier | [6 empty] | Date of For Construction BC installation drawings
|  | Installation company | [10 empty] | Special remarks
Installed by
Inspected by
Barrier Cables at the ramp along line:
|  | Specified spacing between cables | Specified distance from top of slab to middle of topmost cable | Surface mounted steel members secured to columns per dwgs | Job site or pre-installed anchorages have fully seated wedges | Stressed to BC force indicated on dwgs | Back stressed to force indicated on dwgs | Restoration of corrosion protection after back stressing | Strand tails finished | Sealing of sleeves in columns | Initials of inspector or installer | Date | Holes: Topmost cable #1 Bottom cable # varies | Non-compliance items corrected | Initials of inspector or installer | Date
Ramp | to
|  |  | Specified Jacking Force (kips): |  |  |  |  | Specified Gauge Reading (psi): |  |  |  |  | Specified Back stressing Force (kips): |  |  | Cable Numbers:
Level | to
Level | to
Level | to
Level | to
Level | to
Flat | to
Level
Level
Level
Level
Level
Stressing
Spacing / Height
Fixed-End
Finishing
Inspection
Non-compliance / notes
Follow-up (if needed)
Notes

## Example Ramped Slabs
Inspection of Barrier Cable Installation Through or Attached to Concrete Columns | [18 empty] | Page _______ of _________
|  |  |  | Project Name | [10 empty] | Project #
|  |  |  | Site Address | [10 empty] | Date
Jack Serial #
|  |  |  | General contractor | [10 empty] | Gauge Serial #
|  |  |  | Barrier cable supplier | [6 empty] | Date of For Construction BC installation drawings
|  |  |  | Installation company | [10 empty] | Special remarks
Installed by
Inspected by
Barrier Cables at the ramp along line: | [6 empty] | C
|  |  |  | Specified spacing between cables | Specified distance from top of slab to middle of topmost cable | Surface mounted steel members secured to columns per dwgs | Job site or pre-installed anchorages have fully seated wedges | Stressed to BC force indicated on dwgs | Back stressed to force indicated on dwgs | Restoration of corrosion protection after back stressing | Strand tails finished | Sealing of sleeves in columns | Initials of inspector or installer | Date | Holes: Topmost cable #1 Bottom cable # varies | Non-compliance items corrected | Initials of inspector or installer | Date
Ramp | 3 | to | 20
[5 empty] | Specified Jacking Force (kips): | 3.5 |  |  |  | Specified Gauge Reading (psi): | 900 |  |  |  | Specified Back stressing Force (kips): | 33 |  | Cable Numbers: | #1 - #6 and #10 - #11
Level | 1 | to | 2 | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | DJS | 2013-10-25 | Cable #5 did not get galvanized coating | Yes | PS | 2013-11-15 | Cable was covered with galvanized coating
Level | 2 | to | 3 | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | DJS | 2013-10-25 | Cable #3 was not back stressed | Yes | DH | 2013-11-02 | Cable was back stressed & corrosion protected
Level | 3 | to | 4 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | DJS | 2013-10-25
Level | 4 | to | 5 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | DJS | 2013-10-25
Level | 5 | to | 6 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | DJS | 2013-10-25 | Cable #6 needs pocket grouted | Yes | DJS | 2013-10-30
Flat | 3 | to | 20
Level | 2 |  |  | Yes | Yes | Yes | Yes | No | No | No | No | N/A | DJS | 2013-10-25 | Cables #1 thru #11 were not stressed or finished | Yes | DH | 2013-11-02 | All 4 non-compliance items were corrected
Level | 3 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | N/A | DJS | 2013-10-25
Level | 4 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | N/A | DJS | 2013-10-25 | Cables #10 & #11 did not get galvanized coating | Yes | PS | 2013-11-08 | Both cables were covered with galvanized coating
Level | 5 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | N/A | DJS | 2013-10-25
Level | 6 |  |  | Yes | Yes | Yes | Yes | Yes | Yes | DH | Yes | N/A | DJS | 2013-10-25
Stressing
3
20
C
B
Spacing / Height
Fixed-End
Finishing
Inspection
Non-compliance / notes
Follow-up (if needed)
Notes
N